## Full Documentation List (2) (hidden)
AS00N (AR882) | [5 empty] | Langhua | Sobi / Arthrosi |  | Note
| Document name | Est. date needed | Responsible person | Status | Client Review/Approval | First draft | Review | Approve
Verification/Study | Establish WT04N stability (holding time) study protocol | 2026-06-20 | Jing Zhou | Completed | Yes | 2026-05-07 | 2026-06-03 | 2026-06-08 | Approved
Verification/Study | Establish DF02N stability (holding time) study protocol | 2026-06-20 | Jing Zhou | Completed | Yes | 2026-05-07 | 2026-06-03 | 2026-06-08 | Approved
Change | Scale-up Change for AS00N in Workshop A9 | 2026-07-10 | Xubo Zheng | Ongoing | Yes | 2026-06-15 | 2026-06-22 | 2026-07-04 | Updated vesion is provided on June 27,2026 and is under review by customer
| DF02N Appearance change control | 2026-07-13 |  | Ongoing | Yes | 2026-07-08 | 2026-07-10 | 2026-07-13 | Under drafting by Langhua
VMP | Establish Validation Master Plan of AS00N(AR882) | 2026-07-25 | Ling Lin | Ongoing | Yes | 2026-06-09 | 2026-06-16 | 2026-06-30 | Updated vesion is provided on June 26,2026 and is under review by customer
| Establish Validation Master Report of AS00N(AR882) | 2027-03-10 | Ling Lin | To be start | Yes | 2027-02-18 | 2027-02-25 | 2027-03-04
SPEC/Methods | Analytical method validation / verification for AS00N (AR882) | 2026-07-20 | Jing Zhou | N/A | No | N/A | N/A | N/A
| Update relevant analytical methods for AS00N (AR882) | 2026-07-20 | Jing Zhou | N/A | No | N/A | N/A | N/A
| Update IPC specs | 2026-07-20 | Ling Lin | Ongoing | Yes | 2026-07-05 | 2026-07-12 | 2026-07-19 | Updated based on customer comments
| WT04N | 2026-07-20 | Ling Lin | Ongoing | Yes | 2026-07-05 | 2026-07-12 | 2026-07-19 | Under drafting by Langhua
| Update AS00N spec. | 2026-07-20 | Ling Lin | Ongoing | Yes | 2026-07-05 | 2026-07-12 | 2026-07-19 | Under drafting by Langhua
Process/ Cleaning Documents | Update Master Production Instructions of AS00N (AR882) | 2026-07-25 | Li Ji | N/A | No | N/A | N/A | N/A
| Update SOP of Master Production Instructions of AS00N (AR882) | 2026-07-25 | Li Ji | N/A | No | N/A | N/A | N/A
| Establish the MBR of AS01N | 2026-07-25 | Li Ji | Ongoing | Yes | 2026-06-26 | 2026-07-03 | 2026-07-13 | Under drafting by Langhua, expected to be uploaded to the sharepoint on July 2, 2026
| Establish the MBR of AS02N | 2026-07-25 | Li Ji | Ongoing | Yes | 2026-06-30 | 2026-07-07 | 2026-07-17 | Under drafting by Langhua, expected to be uploaded to the sharepoint on July 4, 2026
| Establish the MBR of AS00N | 2026-07-25 | Li Ji | Ongoing | Yes | 2026-07-03 | 2026-07-10 | 2026-07-20 | Under drafting by Langhua, expected to be uploaded to the sharepoint on July 7, 2026
| Update SOP of Equipment cleaning of AS00N (AR882) | 2026-07-20 | Li Ji | N/A | No | N/A | N/A | N/A
| Update Equipment cleaning record of AS00N (AR882) | 2026-07-20 | Li Ji | N/A | No | N/A | N/A | N/A
Validation/ Study | Establish PPQ protocol for AS00N(AR882) | 2026-07-25 | Hongyang Ran | Ongoing | Yes | 2026-06-09 | 2026-06-16 | 2026-06-30 | Updated vesion is provided on June 26,2026 and is under review by customer
| Establish PPQ interim report for AS00N(AR882) | 2026-09-24 | Hongyang Ran | To be start | Yes | 2026-09-20 | 2026-09-22 | 2026-09-24
| Establish PPQ report for AS00N(AR882) | 2027-01-23 | Hongyang Ran | To be start | Yes | 2027-01-04 | 2027-01-11 | 2027-01-18
| Establish the drying profile study protocol for AS00N(AR882) | 2026-07-25 | Hongyang Ran | To be start | Yes | 2026-07-01 | 2026-07-06 | 2026-07-20 | Langhua has been uploaded to the sharepoint on June 18, 2026, and is under review by customer
| Establish the homogeneity study protocol for AS00N(AR882) | 2026-07-25 | Xubo Zheng | To be start | Yes | 2026-07-01 | 2026-07-06 | 2026-07-20 | Langhua has been uploaded to the sharepoint on June 18, 2026, and is under review by customer
| Establish the drying profile study report for AS00N(AR882) | 2027-01-23 | Xubo Zheng | To be start | Yes | 2026-12-25 | 2027-01-09 | 2027-01-16
| Establish the homogeneity study report for AS00N(AR882) | 2027-01-23 | Xubo Zheng | To be start | Yes | 2027-01-15 | 2027-01-18 | 2027-01-21
| Establish the stability study protocol for AS00N(AR882) | 2026-07-31 | Jing Zhou | Ongoing | Yes | 2026-07-06 | 2026-07-13 | 2026-07-23 | Langhua has been uploaded to the sharepoint on June 20, 2026, and is under review by customer
| Establish the holding time study protocol for AS01N, AS02N and AS00N dried product | 2026-07-31 | Xubo Zheng | Ongoing | Yes | 2026-07-06 | 2026-07-13 | 2026-07-23 | Langhua has been uploaded to the sharepoint on June 20, 2026, and is under review by customer
| Establish Cleaning Validation Protocol for AS00N (AR882) | 2026-07-29 | Li Ji | Ongoing | Yes | 2026-07-10 | 2026-07-17 | 2026-07-27 | Under drafting by Langhua
| Establish Cleaning Validation Report for AS00N(AR882) | 2027-03-31 | Li Ji | To be start | Yes | 2027-01-26 | 2027-02-02 | 2027-02-17
Assessment | Establish Risk Assessment for Introduction of AS00N (AR882) in workshop A9 | 2026-07-20 | Hongyang Ran | Ongoing | No | N/A | N/A | N/A
| Update Risk assessment for shared production in Workshop A9 | 2026-07-20 | Hongyang Ran | Ongoing | No | N/A | N/A | N/A
| Establish Risk Assessment for Foreign matter Contamination of AS00N (AR882) in workshop A9 | 2026-07-20 | Hongyang Ran | Ongoing | No | N/A | N/A | N/A
| Establish Equipment Suitability Assessment Report of AS00N (AR882) Production Line in workshop A9 | 2026-07-20 | Ye Tao | Ongoing | No | N/A | N/A | N/A
| Establish CA report of AS00N (AR882) | 2026-07-20 | Zongjun Liu | Ongoing | No | N/A | N/A | N/A
| Establish the risk assessment of cleaning carryover before production, based on the assessment to determine whether the cleaning verification is necessary | 2026-07-25 | Xubo Zheng | Ongoing | No | N/A | N/A | N/A
| Establish Rationality Evaluation of Batch Selection for Process Performance Qualification of AS00N (AR882) in workshop A9 | 2026-07-25 | Ling Lin | Ongoing | No | N/A | N/A | N/A
| Update Risk assessment report for simultaneous production of AS00N and BJ04K in workshop A9 | 2026-07-31 | Hongyang Ran | Ongoing | No | N/A | N/A | N/A
| Establish Assessment Report for Shipping Condition of AS00N (AR882) | 2026-09-30 | Qiuqin Xiang | Ongoing | No | N/A | N/A | N/A
| Establish Genotoxic impurities Assessment Report in AS00N(AR882) | 2027-01-31 | Ling Lin | To be start | No | N/A | N/A | N/A
| Establish Impurity profile for AS00N(AR882) | 2027-01-31 | Ling Lin | To be start | No | N/A | N/A | N/A
| Establish Elemental impurities Assessment Report in AS00N(AR882) | 2027-01-31 | Ling Lin | To be start | No | N/A | N/A | N/A
| Establish Nitrosamine impurities Assessment in AS00N(AR882) | 2027-01-31 | Ling Lin | To be start | No | N/A | N/A | N/A
N/A | Update Approved Supplier List of AS00N (AR882) | 2027-02-28 | Zidan Wu | To be start | No | N/A | N/A | N/A
N/A | Establish PID for AS00N (AR882) equipment | 2026-07-20 | Wanqin Li | Completed | No | N/A | N/A | N/A
CPV | Establish CPV protocol for AS00N (AR882) | 2027-03-31 | Hongyang Ran | To be start | No | N/A | N/A | N/A
Formulas:
Sobi / Arthrosi = [Langhua]+7
Approve = [Sobi / Arthrosi]+12

## Project Plan
Project ID | ABC123
Start Date | 2026-08-25
Finish Date | 2026-11-19
Project Period | 86
Gantt ChABCt (Time Unit) | Day
Project Plan |  | Tech Transfer+Method Transfer & Qualification+10 kg DS Manufacturing
Work Scope | Task ID | Task Description | Owner | Start Date | Finish Date | Duration | Status | Note
|  | Tech Transfer |  | 2026-08-31 | 2026-09-27 | 28 | Ongoing
non-GMP Process Documentation | ABC-001 | Raw Material List provided by CMC | Wayne | 2026-08-31 | 2026-08-31 | 1 | Completed
| ABC-002 | Process Documents provided by CMC | Wayne | 2026-08-31 | 2026-09-07 | 8 | Completed
| ABC-003 | Step 6 MBR Finalization | Wayne/Jackey | 2026-08-31 | 2026-09-09 | 10 | Completed
| ABC-004 | Step 7 MBR Finalization | Wayne/Jackey | 2026-09-10 | 2026-09-14 | 5 | Completed
| ABC-005 | Step 8 MBR Finalization | Wayne/Jackey | 2026-09-15 | 2026-09-19 | 5 | Completed
| ABC-006 | Step 9 MBR Finalization | Wayne/Jackey | 2026-09-20 | 2026-09-27 | 8 | Completed
| ABC-007 | Step 1 MBR Finalization | Wayne/Jackey | 2026-08-31 | 2026-09-09 | 10 | Completed
| ABC-008 | Step 2 MBR Finalization | Wayne/Jackey | 2026-09-10 | 2026-09-14 | 5 | Completed
|  | Method Transfer & Qualification |  | 2026-09-04 | 2026-11-26 | 84 | Ongoing
Method Transfer&Qualification | ABC-009 | non-GMP Method Documents Transfer | Sherry | 2026-09-04 | 2026-09-09 | 6 | Completed
| ABC-010 | GMP Method Documents & Template Transfer | Sherry | 2026-09-04 | 2026-09-07 | 4 | Completed
| ABC-011 | Analytical Material List provided by CMC | Sherry | 2026-09-04 | 2026-09-07 | 4 | Completed
| ABC-012 | Qualification Protocol for GMP Production | Sherry/Lynn | 2026-09-08 | 2026-09-24 | 17 | Ongoing
| ABC-013 | Scope&Parameters Confirmed by ABC | ABC/Sherry | 2026-09-07 | 2026-09-10 | 4 | Completed
| ABC-014 | Qualification Protocol Review and Approval by ABC | ABC/Jane | 2026-09-23 | 2026-09-30 | 8 | Ongoing
| ABC-015 | Method Qualification Experiments | Sherry/Lynn | 2026-10-20 | 2026-11-20 | 32 | To be start
| ABC-016 | Qualification Report Review and Approval by ABC | ABC/Jane | 2026-11-21 | 2026-11-26 | 6 | To be start
|  | Materials Purchasing & Preparation |  | 2026-09-04 | 2026-10-17 | 44 | Ongoing
Purchasing | ABC-017 | GMP materials purchasing and release | Zoey | 2026-09-04 | 2026-09-10 | 7 | Ongoing
RSM Batch Release | ABC-018 | Regulatory Starting Material Batch Release for XYZ001-D(step 2) | Amy | 2026-09-30 | 2026-10-13 | 14 | Ongoing
| ABC-019 | Regulatory Starting Material Batch Release for XYZ001-G(step 9) | Amy | 2026-10-08 | 2026-10-17 | 10 | Ongoing
|  | Side Chain1 Production(non-GMP) |  | 2026-09-10 | 2026-09-14 | 5 | Completed
XYZ001-C | ABC-020 | Step 6 Production(XYZ001-H → XYZ001-C ) | Wayne | 2026-09-10 | 2026-09-14 | 5 | Completed
| ABC-021 | Step 6 Synthesis&IPC in Taizhou Langhua | Jackey/Lily Chen | 2026-09-10 | 2026-09-14 | 5 | Completed
|  | Side Chain 2 Production(non-GMP) |  | 2026-09-15 | 2026-10-05 | 21 | Completed
XYZ001-K | ABC-022 | Step 7 Production(XYZ001-J → XYZ001-K ) | Wayne | 2026-09-15 | 2026-09-19 | 5 | Completed
| ABC-023 | Step 7 Synthesis&IPC in Taizhou Langhua | Jackey/Lily Chen | 2026-09-15 | 2026-09-19 | 5 | Completed
XYZ001-M | ABC-024 | Step 8 Production(XYZ001-K → XYZ001-M ) | Wayne | 2026-09-20 | 2026-09-27 | 8 | Completed
| ABC-025 | Step 8 Synthesis&IPC in Taizhou Langhua | Jackey/Lily Chen | 2026-09-20 | 2026-09-27 | 8 | Completed
XYZ001-G(RSM) | ABC-026 | Step 9 Production(XYZ001-M → XYZ001-G ) | Wayne | 2026-09-28 | 2026-10-05 | 8 | Completed
| ABC-027 | Step 9 Synthesis&IPC in Taizhou Langhua | Jackey/Lily Chen | 2026-09-28 | 2026-10-05 | 8 | Ongoing
|  | Main Chain Production (non-GMP) |  | 2026-09-07 | 2026-09-19 | 13 | Completed
XYZ001-B | ABC-028 | Step 1 Production(XYZ001-A → XYZ001-B ) | Wayne | 2026-09-10 | 2026-09-14 | 5 | Completed
| ABC-029 | Step 1 Synthesis&IPC in Taizhou Langhua | Jackey/Lily Chen | 2026-09-10 | 2026-09-14 | 5 | Completed
XYZ001-D(RSM) | ABC-030 | Step 2 Production(XYZ001-B → XYZ001-D ) | Wayne | 2026-09-15 | 2026-09-19 | 5 | Completed
| ABC-031 | Step 2 Synthesis&Starting Material Batch Release for XYZ001-D | Jackey/Lily Chen | 2026-09-15 | 2026-09-19 | 5 | Completed
|  | Main Chain Production (GMP) |  | 2026-09-07 | 2026-12-12 | 97 | To be start
Mock Audit | ABC-032 | Potential Mock Audit by ABC | Joyce/Cherry | TBD | TBD | TBD | To be start
EHS | ABC-033 | Process Safety Assessment | Lucas/Wayne | 2026-09-15 | 2026-10-10 | 26 | Ongoing
XYZ001-E |  | Step 3(XYZ001-D → XYZ001-E ) |  | 2026-09-07 | 2026-10-20 | 44 | To be start
| ABC-034 | Step 3 MBR drafted by Taizhou Langhua | Zoey | 2026-09-07 | 2026-10-05 | 29 | Ongoing
| ABC-035 | Step 3 MBR review and approval by ABC | ABC/Lynn | 2026-10-06 | 2026-10-15 | 10 | To be start
| ABC-036 | Step 3 GMP Production | Zoey | 2026-10-16 | 2026-10-20 | 5 | To be start
XYZ001-F |  | Step 4(XYZ001-E → XYZ001-F) |  | 2026-09-07 | 2026-10-25 | 49 | To be start
| ABC-037 | Step 4 MBR drafted by Taizhou Langhua | Zoey | 2026-09-07 | 2026-10-05 | 29 | Ongoing
| ABC-038 | Step 4 MBR review and approval by ABC | ABC/Lynn | 2026-10-06 | 2026-10-15 | 10 | To be start
| ABC-039 | Step 4 GMP Production | Zoey | 2026-10-21 | 2026-10-25 | 5 | To be start
XYZ001.P1(ABC352) |  | Step 5(XYZ001-F → XYZ001.P1 ) |  | 2026-09-07 | 2026-11-08 | 63 | To be start
| ABC-040 | Step 5 MBR drafte by Taizhou Langhua | Zoey | 2026-09-07 | 2026-10-05 | 29 | To be start
| ABC-041 | Step 5 MBR review and approval by ABC | ABC/Lynn | 2026-10-06 | 2026-10-15 | 10 | To be start
| ABC-042 | Step 5 GMP Production | Zoey | 2026-10-26 | 2026-11-08 | 14 | To be start
| ABC-043 | API Batch Release | Lynn/Sherry | 2026-11-26 | 2026-12-09 | 14 | To be start
| ABC-044 | API Shipment | Amy | 2026-12-10 | 2026-12-12 | 3 | To be start
Formulas:
Start Date = MIN([Start Date, row below]:E19)
Start Date = MIN([Start Date, row below]:[Start Date, row below])
Finish Date = MAX([Finish Date, row below]:F19)
Finish Date = MAX([Finish Date, row below]:[Finish Date, row below])

## QC Documentation List
XYZ001.P1(ABC123) | [5 empty] | Langhua | ABC |  | Note
| Document name | Est. date needed | Responsible person | Status | Client Review/Approval | First draft | Review | Approve
Specifications | Spec of LHA021.P1 | 2026-10-08 |  | Ongoing | Yes | 2026-09-29 | 2026-09-29 | 2026-10-08
Reference Standard Qualification | Reference standard qualification protocol | 2026-08-30 |  | Completed | No | / | Yes | No | COA is ready
| Structure confirmation report | 2026-11-13 |  | To be start | Yes | 2026-10-23 | 2026-10-23 | 2026-11-13
Stability-indicating Method Development | Method development report including forced degradation study | 2026-12-09 |  | To be start | Yes | 2026-11-25 | 2026-11-25 | 2026-12-09
Method Documents | RD method: Assay and related substances | 2026-10-17 |  | To be start | Yes | 2026-10-10 | 2026-10-10 | No | The RD methods do not require ABC signature
| RD method: Chiral purity | 2026-10-19 |  | To be start | Yes | 2026-10-12 | 2026-10-12 | No
| RD method: Residual solvents | 2026-10-18 |  | To be start | Yes | 2026-10-09 | 2026-10-09 | No
| RD method: Elemental Impurities Determination Method | 2026-10-16 |  | To be start | Yes | 2026-10-09 | 2026-10-09 | No
| RD method: Particle Size Determination Method | 2026-10-20 |  | To be start | Yes | 2026-10-13 | 2026-10-13 | No
| RD method: Microbial Limit Test Method | 2026-10-15 |  | To be start | Yes | 2026-10-08 | 2026-10-08 | No
| GMP release method: Assay and related substances | 2026-11-16 | Hongyang Ran | To be start | Yes | 2026-11-02 | 2026-11-02 | 2026-11-16
| GMP release method: Chiral purity | 2026-11-16 | Hongyang Ran | To be start | Yes | 2026-11-04 | 2026-11-04 | 2026-11-16
| GMP release method: Residual solvents | 2026-11-17 | Hongyang Ran | To be start | Yes | 2026-11-05 | 2026-11-05 | 2026-11-17
| GMP release method: Elemental Impurities Determination Method | 2026-11-11 | Hongyang Ran | To be start | Yes | 2026-10-30 | 2026-10-30 | 2026-11-11
| GMP release method: Particle Size Determination Method | 2026-11-08 |  | To be start | Yes | 2026-10-28 | 2026-10-28 | 2026-11-08
| GMP release method: Microbial Limit Test Method | 2026-11-18 | Xubo Zheng | To be start | Yes | 2026-11-06 | 2026-11-06 | 2026-11-18
Mehotd Qualification | Qualification protocol of Assay and related substances | 2026-10-17 |  | To be start | Yes | 2026-10-10 | 2026-10-10 | 2026-10-17
| Qualification protocol of Chiral purity | 2026-10-19 |  | To be start | Yes | 2026-10-12 | 2026-10-12 | 2026-10-19
| Qualification protocol of Residual solvents | 2026-10-18 |  | To be start | Yes | 2026-10-09 | 2026-10-09 | 2026-10-18
| Qualification protocol of Elemental Impurities Determination Method | 2026-10-16 |  | To be start | Yes | 2026-10-09 | 2026-10-09 | 2026-10-16
| Qualification protocol of Particle Size | 2026-10-20 |  | To be start | Yes | 2026-10-13 | 2026-10-13 | 2026-10-20
| Qualification protocol of Microbial Limit Test Method | 2026-10-15 |  | To be start | Yes | 2026-10-08 | 2026-10-08 | 2026-10-15
| Qualification report of Assay and related substances | 2026-11-16 | Hongyang Ran | To be start | Yes | 2026-11-02 | 2026-11-02 | 2026-11-16
| Qualification report of Chiral purity | 2026-11-16 | Hongyang Ran | To be start | Yes | 2026-11-04 | 2026-11-04 | 2026-11-16
| Qualification report of Residual solvents | 2026-11-17 | Hongyang Ran | To be start | Yes | 2026-11-05 | 2026-11-05 | 2026-11-17
| Qualification report of Elemental Impurities Determination Method | 2026-11-11 | Hongyang Ran | To be start | Yes | 2026-10-30 | 2026-10-30 | 2026-11-11
| Qualification report of Particle Size | 2026-11-08 |  | To be start | Yes | 2026-10-28 | 2026-10-28 | 2026-11-08
| Qualification report of Microbial Limit Test Method | 2026-11-18 | Xubo Zheng | To be start | Yes | 2026-11-06 | 2026-11-06 | 2026-11-18
Stability study | Stability study protocol | 2027-01-06 |  | To be start | Yes | 2026-11-01 | 2027-12-18 | 2027-01-06
| Stability study report | TBD |  | To be start | Yes | TBD | TBD | TBD

## 已完成-行动项 (hidden)
序列 | 内容 | 状态 | 开始日期 | 完成日期 | 责任人 | 备注
1 | 制定供应商审计计划，QA提供客供料RM1 & RM2引用客户审计报告的需求清单 | 已完成 | 2022-09-30 | 2022-10-12 | 吴春华，小兰 | 2022/10/12：QA 已经提供 PMO提醒客户提供客供料审计相关信息与资料
2 | 客户确认按照更换后的路线（AQCD）进行工艺开发，以前面2~3周对step2和step3进行工艺参数摸索获得的信息，在新步骤中确认，并以新产生的数据为基础finalize。（其他步骤未发生变化，请在现有变更的基础上评估变更后影响） | 已完成 | 2022-10-05 | 2022-10-23 | 沈海波
3 | 提供所需杂质时间计划表 | 已完成 | 2022-10-05 | 2022-10-15 | 韩叶华 | 2022/10/13: 已完成
4 | PV 所需设备 材质 时间计划表 | 已完成 | 2022-10-05 | 2022-10-15 | 沈海波 赵中良
5 | 客户提供客供料RM1 & RM2审计报告（QA已提供需求清单） | 已完成 | 2022-10-05 | 2022-10-30 | PMO
6 | RM3 供应商审计启动时间计划 | 已完成 | 2022-10-05 | 2022-10-20 | 王小兰 | 2022/10/13: 已给出相关意见，需要三批原料验证，与供应商沟通后，顺利的话审计周期需20天，供应商审计资料提前准备
7 | 统计RSM的批次，批量并制定与PV生产批对批的策略 | 已完成 | 2022-10-05 | 2022-10-12 | 赵中良，吴春华 | 2022/10/12：RSM 原料验证需要三批
8 | 丙基磺酰氯的供应商信息反馈给PMO | 已完成 | 2022-10-12 | 2022-10-20 | 沈海波 尹鹏 | 2022/10/20：研发提供备选的3家（ 丙基磺酰氯）采购供应商信息，如下：a)江西国化实业有限公司（目前生产批次使用的供应商）b) 寿光诺盟化工有限公司（已经提供500g小样）c) 上海玉雕化学技术有限公司（不能提供小样，且,吨位起订）
9 | 客户建议第二批 GMP 2月底放行-时间计划表需更新 | 已完成 | 2022-10-12 | 2022-10-20 |  | 2022/10/20：与客户确认后，时间么有问题
11 | 该批次中抽出部分产品进行 纯化+标化 后作为对照品（130 g +20 g 制剂），预计10.24 完成 | 已完成 | 2022-10-12 | 2022-10-24 | 韩叶华 沈海波 | 2022/10/24：已完成制备，COA已发给客户确认，并寄2.0 g给客户。2022/10/12：目前正在做50 g规模
13 | 博腾准备启动调查报告，调查成品磨粉后含量由98.8 %降为 98.2%的具体原因，同时收集与含量相关的数据反馈于客户，并同时进行返工结晶。 | 已完成 | 2022-10-12 | 2022-11-01 | 韩叶华 陈晓霖 | 2022/11/1：在全检放行。2022/10/22：D290-F再加工 R干品出料24.92 kg，预计25号磨粉小试。 2022/10/12：先返工，调查同时进行。2022/10/9:调查继续进行，样品返工纯化化，客户希望24号产品反馈至制剂端。 2022/9/30: QC初步调查没有问题，准备启动技术和研发调查 | 工艺原因：D290-B步骤产生的PMB副产物，在D290-B、D290-C、D290-D中未监测到，并且工艺去除能力有限，也未进行相应的纯化操作。导致该杂质进入到D290-F中，而D290-F的工艺对该杂质的去除能力也不高，而D290-F至D290步骤只是磨粉操作，没有除杂能力，最终导致D290成品含量偏低，其接近标准范围下限。D290-F工艺对杂质处理能力有限，不能完全将核磁图谱中6.5~7.0处是有的未知杂质完全去除，从而导致103582-105-00002(汉霖批次)含量偏低。
14 | QRA 研究中间体物料数量的预留计划 | 已完成 | 2022-10-12 | 2022-11-02 | 沈海波 | 2022/11/2：自己备料。2022/10/19：待沈海波与客户确定。
10 | 按照注册申报要求，提供RSM、关键物料的名称以及供应商信息 | 已完成 | 2022-10-20 | 2022-10-20 | 沈海波 | 2022/10/19；关键物料与客户进行沟通没有关键物料—跟TC客户沟通。供应商信息给PMO，反馈给采购提前收集相关数据。2022/10/12：需研发收集数据反馈 RM3 供应商信息
12 | 确认D290-A杂质信息 | 已完成 | 2022-10-26 | 2022-10-26 | 沈海波 尹鹏 | 2022/10/26：D290-A 两个杂质 给到分析50 g。
15 | 确认Demo 是否可以分段进行生产 | 已完成 | 2022-10-26 | 2022-10-27 | 张栋 | 2022/10/27：已确认分段方案可行
17 | RSM 分批排产计划 | 已完成 | 2022-10-26 | 2022-10-26 | 李祥福 | 2022/10/26: 四批生产for Demo,PV
18 | 与客户确认API 是否需要增加粗品结晶工艺 | 已完成 | 2022-10-26 | 2022-10-28 | 周琪 | 2022/10/28：与客户确认需要增加
16 | 关于RSM 分批计划，SPOC ,summer 内部讨论确认其可行性 | 已完成 | 2022-11-02 | 2022-11-02 | 张栋 | 邮件已确认
5 | 17 kg毒理批 生产计划 | 已完成 | 2022-10-12 | 2022-11-09 | 沈海波 赖伟 | 2022/11/9：曾泉文已经排产了。2022/10/19：报价的同时正在预约产能
7 | 最后2步的最终工艺确认工作（D290-D）转移至岩博团队 | 已完成 | 2022-10-12 | 2022-10-26 | 沈海波 陈岩 卢亮 | 2022/10/26：最后两步已转移至岩博团队，最终工艺确认正在进行。

## PV排产计划表-原始 (hidden)
设备 | 生产车间 | 步骤 | 状态 | 外观 | 体积/m³ | 单步周期 | 210446 | 技术批 | PV1 | PV2 | PV3 | PV设备（差异）
R-A2086（GL 1000L） | WS102 | D290-A | 中间体 | 固体 | 4 | 5 | 生产批次 | 1 | 1 | 2 | 3 | ——
C-A2106（Halar） | WS101 | [5 empty] | 投料量/KG
G-A1009（GL 3000L） | [6 empty] | 开始时间 | 2023-01-19 | 2023-03-30 | 2023-04-06 | 2023-04-13
[7 empty] | 结束时间 | 2023-01-23 | 2023-04-03 | 2023-04-10 | 2023-04-17
产出量/KG
R-A2087（GL 1500L） | WS102 | D290-B | 中间体 | 液体 | 4.5 | 4 | 生产批次 | 1 | 1 | 2 | 3 | ——
R-A2081（GL 3000L） | [6 empty] | 投料量/KG
[7 empty] | 开始时间 | 2023-01-30 | 2023-04-06 | 2023-04-21 | 2023-05-06
[7 empty] | 结束时间 | 2023-02-02 | 2023-04-09 | 2023-04-24 | 2023-05-09
产出量/KG
R-A2087（GL 1500L） | WS102 | D290-C湿品 | 中间体 | 固体 | 4.5 | 6 | 生产批次 | 1 | 1 | 2 | 3 | ——
R-A2081（GL 3000L） | [6 empty] | 投料量/KG
C-A2128（Halar） | [6 empty] | 开始时间 | 2023-02-05 | 2023-04-12 | 2023-04-27 | 2023-05-12
[7 empty] | 结束时间 | 2023-02-10 | 2023-04-17 | 2023-05-02 | 2023-05-17
产出量/KG
R-A2093（GL 2000L） | WS102 | D290-D | 中间体 | 固体 | 8 | 7 | 生产批次 | 1 | 1 | 2 | 3 | C-A2131（Halar φ800）
R-A2091（GL 3000L） | [6 empty] | 投料量/KG
C-A3105（Halar φ800）+压滤器 | [6 empty] | 开始时间 | 2023-02-13 | 2023-05-17 | 2023-05-25 | 2023-06-02
G-A2008（GL 3000L） | [6 empty] | 结束时间 | 2023-02-19 | 2023-05-23 | 2023-05-31 | 2023-06-08
产出量/KG
R-A2088（GL 1500L） | WS102 | D290-F乙酸乙酯溶液 | 中间体 | 液体 | 4.5 | 7 | 生产批次 | 1 | 1 | 2 | 3 | ——
R-A6088（GL 3000L） | [6 empty] | 投料量/KG
[7 empty] | 开始时间 | 2023-02-22 | 2023-05-27 | 2023-06-06 | 2023-06-16
[7 empty] | 结束时间 | 2023-02-28 | 2023-06-02 | 2023-06-12 | 2023-06-22
产出量/KG
R-A1016（GL 2000L） | WS101 | D290-F | 中间体 | 固体 | 4.08 | 6 | 生产批次 | 1 | 1 | 2 | 3 | ——
R-A1017（HC 2000L） | [6 empty] | 投料量/KG
C-A1086（HAC） | [6 empty] | 开始时间 | 2023-03-09 | 2023-06-10 | 2023-06-17 | 2023-06-24
B-A1192（HAC 75.6L） | [6 empty] | 结束时间 | 2023-03-14 | 2023-06-15 | 2023-06-22 | 2023-06-29
产出量/KG
B-A1193（气流粉碎机 SS） | WS101 | D290 | 成品 | 固体 | —— | 5 | 生产批次 | 1 | 1 | 2 | 3 | ——
投料量/KG
[7 empty] | 开始时间 | 2023-03-16 | 2023-06-29 | 2023-07-07 | 2023-07-15
[7 empty] | 结束时间 | 2023-03-20 | 2023-07-03 | 2023-07-11 | 2023-07-19
[7 empty] | 产出量/KG | 25 | 25 | 25 | 25

## 15 kg 毒理批排产计划表-221115 已完成 9.38 (hidden)
因上次25 kg 批次D290-A因收率低，重投了一锅得到的D290-A产品37 Kg 直接用于此次的毒理批生产,D290
15 kg毒理批产能计划如下:.
步骤 | 生产车间 | 计划生产时间 | 设备1 | 设备2
D290-C湿品 | 104车间 | 10.14~10.18 | R-A4028（GL 1000L） | R-A4023（GL 1500L）
D290-D粗湿品 | 104车间 | 10.18~10.21 | R-A4028（GL 1000L） | ——
D290-D湿品 | 304车间 | 10.21~10.23 | R-FA4067（GL 100L） | ——
D290-D | 304车间 | 10.23~10.25 | 根据项目进度随时跟进干燥设备
D290-F乙酸乙酯溶液 | 104车间 | 10.28~11.02 | R-A4028（GL 1000L） | ——
D290-F湿品 | 技术部公斤级实验室 | 11.02~11.05 | 50L玻璃釜*2 | ——
D290-F | 304 | 11.06~11.7 | 根据项目进度随时跟进干燥设备
D290 | 101 | 11.7~11.10 | B-A1193
(需要根据PSD判断是否需要做磨粉小试)
D290全检 |  | 11.10~11.15
(20221104)计划排产:
步骤 | 操作 | 车间 | 完成时间 | 耗时 | 备注
D290-F乙酸乙酯溶液
D290-F乙酸乙酯溶液 | 浓缩结束 | 104车间 | 2022-11-04 13:00
| 取样中控拿到结果 |  | 2022-11-04 20:00 | 7
| 压滤、过硅胶垫结束 |  | 2022-11-04 22:00 | 2
D290-F乙酸乙酯溶液
D290-F湿品
结晶1次 | 投料开始 | 106车间 | 2022-11-05 13:00
| 浓缩结束 |  | 2022-11-05 21:00 | 8
| 升温转晶结束 |  | 2022-11-06 03:00 | 6
| 降温结束 |  | 2022-11-06 08:00 | 5
| 结晶结束 |  | 2022-11-06 14:00 | 6
| 取样中控结束 |  | 2022-11-06 16:00 | 2 | 不等中控结果
| 压滤/离心 |  | 2022-11-06 19:00 | 5
| 湿品中控 |  | 2022-11-07 19:00 | 24 | 不等中控结果
结晶2次 | 投料 | 106车间 | 2022-11-06 19:00
| 浓缩 |  | 2022-11-07 05:00 | 10
| 升温转晶 |  | 2022-11-07 11:00 | 6
| 降温 |  | 2022-11-07 16:00 | 5
| 结晶 |  | 2022-11-07 22:00 | 6
| 取样中控 |  | 2022-11-08 | 2
| 压滤/离心 |  | 2022-11-08 05:00 | 5
| 湿品中控 |  | 2022-11-09 05:00 | 24 | 不等中控结果
干燥 | 投料 | 304车间 | 2022-11-08 08:00
| 升温干燥 |  | 2022-11-09 08:00 | 24
| 取样中控 |  | 2022-11-09 14:00 | 6
| 出料 |  | 2022-11-09 16:00 | 2
掺杂 | 投料 | 304 | 2022-11-10 16:00 | 24
| 取样中控 |  | 2022-11-11 02:00 | 10
磨粉 | 磨粉投料 | 101车间 | 2022-11-13 09:00
| 磨粉 |  | 2022-11-13 19:00 | 10