## Full Documentation List (2) (hidden)
AS00N (AR882) | [5 empty] | Langhua | Sobi / Arthrosi |  | Note
| Document name | Est. date needed | Responsible person | Status | Client Review/Approval | First draft | Review | Approve
Verification/Study | Establish WT04N stability (holding time) study protocol | 2026-06-20 | Jing Zhou | Completed | Yes | 2026-05-07 | 2026-06-03 | 2026-06-08 | Approved
Verification/Study | Establish DF02N stability (holding time) study protocol | 2026-06-20 | Jing Zhou | Completed | Yes | 2026-05-07 | 2026-06-03 | 2026-06-08 | Approved
Change | Scale-up Change for AS00N in Workshop A9 | 2026-07-10 | Xubo Zheng | Ongoing | Yes | 2026-06-15 | 2026-06-22 | 2026-07-04 | Updated vesion is provided on June 27,2026 and is under review by customer
| DF02N Appearance change control | 2026-07-13 |  | Ongoing | Yes | 2026-07-08 | 2026-07-10 | 2026-07-13 | Under drafting by Langhua
VMP | Establish Validation Master Plan of AS00N(AR882) | 2026-07-25 | Ling Lin | Ongoing | Yes | 2026-06-09 | 2026-06-16 | 2026-06-30 | Updated vesion is provided on June 26,2026 and is under review by customer
| Establish Validation Master Report of AS00N(AR882) | 2027-03-10 | Ling Lin | To be start | Yes | 2027-02-18 | 2027-02-25 | 2027-03-04
SPEC/Methods | Analytical method validation / verification for AS00N (AR882) | 2026-07-20 | Jing Zhou | N/A | No | N/A | N/A | N/A
| Update relevant analytical methods for AS00N (AR882) | 2026-07-20 | Jing Zhou | N/A | No | N/A | N/A | N/A
| Update IPC specs | 2026-07-20 | Ling Lin | Ongoing | Yes | 2026-07-05 | 2026-07-12 | 2026-07-19 | Updated based on customer comments
| WT04N | 2026-07-20 | Ling Lin | Ongoing | Yes | 2026-07-05 | 2026-07-12 | 2026-07-19 | Under drafting by Langhua
| Update AS00N spec. | 2026-07-20 | Ling Lin | Ongoing | Yes | 2026-07-05 | 2026-07-12 | 2026-07-19 | Under drafting by Langhua
Process/ Cleaning Documents | Update Master Production Instructions of AS00N (AR882) | 2026-07-25 | Li Ji | N/A | No | N/A | N/A | N/A
| Update SOP of Master Production Instructions of AS00N (AR882) | 2026-07-25 | Li Ji | N/A | No | N/A | N/A | N/A
| Establish the MBR of AS01N | 2026-07-25 | Li Ji | Ongoing | Yes | 2026-06-26 | 2026-07-03 | 2026-07-13 | Under drafting by Langhua, expected to be uploaded to the sharepoint on July 2, 2026
| Establish the MBR of AS02N | 2026-07-25 | Li Ji | Ongoing | Yes | 2026-06-30 | 2026-07-07 | 2026-07-17 | Under drafting by Langhua, expected to be uploaded to the sharepoint on July 4, 2026
| Establish the MBR of AS00N | 2026-07-25 | Li Ji | Ongoing | Yes | 2026-07-03 | 2026-07-10 | 2026-07-20 | Under drafting by Langhua, expected to be uploaded to the sharepoint on July 7, 2026
| Update SOP of Equipment cleaning of AS00N (AR882) | 2026-07-20 | Li Ji | N/A | No | N/A | N/A | N/A
| Update Equipment cleaning record of AS00N (AR882) | 2026-07-20 | Li Ji | N/A | No | N/A | N/A | N/A
Validation/ Study | Establish PPQ protocol for AS00N(AR882) | 2026-07-25 | Hongyang Ran | Ongoing | Yes | 2026-06-09 | 2026-06-16 | 2026-06-30 | Updated vesion is provided on June 26,2026 and is under review by customer
| Establish PPQ interim report for AS00N(AR882) | 2026-09-24 | Hongyang Ran | To be start | Yes | 2026-09-20 | 2026-09-22 | 2026-09-24
| Establish PPQ report for AS00N(AR882) | 2027-01-23 | Hongyang Ran | To be start | Yes | 2027-01-04 | 2027-01-11 | 2027-01-18
| Establish the drying profile study protocol for AS00N(AR882) | 2026-07-25 | Hongyang Ran | To be start | Yes | 2026-07-01 | 2026-07-06 | 2026-07-20 | Langhua has been uploaded to the sharepoint on June 18, 2026, and is under review by customer
| Establish the homogeneity study protocol for AS00N(AR882) | 2026-07-25 | Xubo Zheng | To be start | Yes | 2026-07-01 | 2026-07-06 | 2026-07-20 | Langhua has been uploaded to the sharepoint on June 18, 2026, and is under review by customer
| Establish the drying profile study report for AS00N(AR882) | 2027-01-23 | Xubo Zheng | To be start | Yes | 2026-12-25 | 2027-01-09 | 2027-01-16
| Establish the homogeneity study report for AS00N(AR882) | 2027-01-23 | Xubo Zheng | To be start | Yes | 2027-01-15 | 2027-01-18 | 2027-01-21
| Establish the stability study protocol for AS00N(AR882) | 2026-07-31 | Jing Zhou | Ongoing | Yes | 2026-07-06 | 2026-07-13 | 2026-07-23 | Langhua has been uploaded to the sharepoint on June 20, 2026, and is under review by customer
| Establish the holding time study protocol for AS01N, AS02N and AS00N dried product | 2026-07-31 | Xubo Zheng | Ongoing | Yes | 2026-07-06 | 2026-07-13 | 2026-07-23 | Langhua has been uploaded to the sharepoint on June 20, 2026, and is under review by customer
| Establish Cleaning Validation Protocol for AS00N (AR882) | 2026-07-29 | Li Ji | Ongoing | Yes | 2026-07-10 | 2026-07-17 | 2026-07-27 | Under drafting by Langhua
| Establish Cleaning Validation Report for AS00N(AR882) | 2027-03-31 | Li Ji | To be start | Yes | 2027-01-26 | 2027-02-02 | 2027-02-17
Assessment | Establish Risk Assessment for Introduction of AS00N (AR882) in workshop A9 | 2026-07-20 | Hongyang Ran | Ongoing | No | N/A | N/A | N/A
| Update Risk assessment for shared production in Workshop A9 | 2026-07-20 | Hongyang Ran | Ongoing | No | N/A | N/A | N/A
| Establish Risk Assessment for Foreign matter Contamination of AS00N (AR882) in workshop A9 | 2026-07-20 | Hongyang Ran | Ongoing | No | N/A | N/A | N/A
| Establish Equipment Suitability Assessment Report of AS00N (AR882) Production Line in workshop A9 | 2026-07-20 | Ye Tao | Ongoing | No | N/A | N/A | N/A
| Establish CA report of AS00N (AR882) | 2026-07-20 | Zongjun Liu | Ongoing | No | N/A | N/A | N/A
| Establish the risk assessment of cleaning carryover before production, based on the assessment to determine whether the cleaning verification is necessary | 2026-07-25 | Xubo Zheng | Ongoing | No | N/A | N/A | N/A
| Establish Rationality Evaluation of Batch Selection for Process Performance Qualification of AS00N (AR882) in workshop A9 | 2026-07-25 | Ling Lin | Ongoing | No | N/A | N/A | N/A
| Update Risk assessment report for simultaneous production of AS00N and BJ04K in workshop A9 | 2026-07-31 | Hongyang Ran | Ongoing | No | N/A | N/A | N/A
| Establish Assessment Report for Shipping Condition of AS00N (AR882) | 2026-09-30 | Qiuqin Xiang | Ongoing | No | N/A | N/A | N/A
| Establish Genotoxic impurities Assessment Report in AS00N(AR882) | 2027-01-31 | Ling Lin | To be start | No | N/A | N/A | N/A
| Establish Impurity profile for AS00N(AR882) | 2027-01-31 | Ling Lin | To be start | No | N/A | N/A | N/A
| Establish Elemental impurities Assessment Report in AS00N(AR882) | 2027-01-31 | Ling Lin | To be start | No | N/A | N/A | N/A
| Establish Nitrosamine impurities Assessment in AS00N(AR882) | 2027-01-31 | Ling Lin | To be start | No | N/A | N/A | N/A
N/A | Update Approved Supplier List of AS00N (AR882) | 2027-02-28 | Zidan Wu | To be start | No | N/A | N/A | N/A
N/A | Establish PID for AS00N (AR882) equipment | 2026-07-20 | Wanqin Li | Completed | No | N/A | N/A | N/A
CPV | Establish CPV protocol for AS00N (AR882) | 2027-03-31 | Hongyang Ran | To be start | No | N/A | N/A | N/A
Formulas:
Sobi / Arthrosi = [Langhua]+7
Approve = [Sobi / Arthrosi]+12

## Project Plan
Project ID | AR882
Start Date | 2026-03-17
Finish Date | 2027-03-10
Project Period | 358
Gantt Chart (Time Unit) | Day
Project Plan
Work Scope | Task ID | Task Description | Owner | Start Date | Finish Date | Duration | Status | Note
|  | Pre-production Preparation |  | 2026-04-01 | 2026-06-26 | 87
Preparation | AR-001 | Coutersigned PO |  | 2026-04-03 | 2026-04-03 | 1 | Completed
| AR-002 | Upfront Payment |  | 2026-04-03 | 2026-04-23 | 21 | Completed
| AR-003 | Quality Agreement | Cherry Chen | 2026-04-07 | 2026-06-10 | 65 | Completed
| AR-004 | Installation / Replacement of 6300L/8000L *2 reactors | Kaiyue Tao | 2026-04-01 | 2026-05-15 | 45 | Completed
| AR-005 | Qualification of 6300L/8000L *2 reactors | Kaiyue Tao | 2026-05-15 | 2026-06-10 | 27 | Completed
| AR-006 | Audit prior to PPQ production | Cherry Chen | 2026-06-23 | 2026-06-26 | 4 | Completed
| AR-007 | PGIs justification report |  | 2026-07-03 | 2026-07-27 |  | Completed
| AR-008 | Investigation on SM2 appearance variations |  | 2026-07-03 | 2026-07-08 |  | Completed
| AR-009 | Use test of SM2 (3 batches) to INT 1 |  | 2026-07-04 | 2026-07-07 |  | Completed
|  | Analytical Method Validation Report |  | 2026-03-24 | 2026-07-25 | 124
SM1 | AR-010 | Method validation report of Water content for SM1 | Jing Zhou | 2026-04-25 | 2026-05-05 | 11 | Completed
| AR-011 | Method validation report of Identification and ROI by FTIR for SM1 | Jing Zhou | 2026-03-24 | 2026-05-10 | 48 | Completed
| AR-012 | Method validation report of Identification by FTIR（ATR) for SM1 | Jing Zhou | 2026-06-17 | 2026-06-30 | 14 | Completed
SM2 | AR-013 | Method validation report of Water content for SM2 | Jing Zhou | 2026-04-25 | 2026-05-05 | 11 | Completed
| AR-014 | Method validation report of Identification and ROI by FTIR for SM2 | Jing Zhou | 2026-03-24 | 2026-05-10 | 48 | Completed
AS03N | AR-015 | Method validation report of particle size for AS03N | Jing Zhou | 2026-07-01 | 2026-07-15 | 15 | Completed
AR882 | AR-016 | Method validation report of Identification by FTIR/Water content of INTs | Jing Zhou | 2026-04-30 | 2026-05-10 | 11 | Completed
| AR-017 | Method validation report of IPC1 (AS01N Reaction Solution) | Jing Zhou | 2026-07-12 | 2026-07-25 | 14 | Completed
| AR-018 | Method validation report of IPC2 (AS01N Reaction Solution) | Jing Zhou | 2026-04-30 | 2026-05-15 | 16 | Completed
| AR-019 | Method validation report of IPC4 (AS02N Reaction Solution) | Jing Zhou | 2026-05-10 | 2026-05-25 | 16 | Completed
| AR-020 | Method validation report of IPC6 (AS00N Reaction Solution) | Jing Zhou | 2026-05-15 | 2026-05-30 | 16 | Completed
| AR-021 | Method validation report of IPC7 & IPC8 (Water content) | Jing Zhou | 2026-04-30 | 2026-05-10 | 11 | Completed
| AR-022 | Method validation report of IPC3, 5 (Residual solvents by HSGC) | Jing Zhou | 2026-04-25 | 2026-05-05 | 11 | Completed
| AR-023 | Method validation report of Coulometric Water content for AR882 | Jing Zhou | 2026-07-07 | 2026-07-20 | 14 | Completed
| AR-024 | Method validation report of Residual Benzene and Dichloromethane by GC | Jing Zhou | 2026-04-01 | 2026-06-11 | 72 | Completed
|  | RSM Manufacture (AR01-SM1 / WT04N) |  | 2026-03-25 | 2026-07-23 | 121
Documentation | AR-025 | Documentation for AR-SM1 manufacture | Ling Lin | 2026-04-07 | 2026-06-15 | 70 | Completed
Material | AR-026 | Materials purchasing | Alex Xu | 2026-03-25 | 2026-04-25 | 32 | Completed
AR01-SM1 Production (last step under GMP, 1136kg) | AR-027 | AR01-3 (2 lots) production | Alex Xu | 2026-04-16 | 2026-04-29 | 14 | Completed
| AR-028 | AR01-4 (3 lots) production | Alex Xu | 2026-04-16 | 2026-05-01 | 16 | Completed
| AR-029 | AR01-6 (4 lots) production | Alex Xu | 2026-04-24 | 2026-05-15 | 22 | Completed
| AR-030 | AR01-7 (7 lots) production | Alex Xu | 2026-05-11 | 2026-06-15 | 36 | Completed
| AR-031 | SM1 (7 lots) production under GMP | Zongjun Liu | 2026-06-16 | 2026-07-18 | 33 | Completed
| AR-032 | Release test of SM1 (1-3 lots) | Jing Zhou | 2026-06-28 | 2026-07-02 | 5 | Completed
| AR-033 | Release test of SM1 (4-7 lots) | Jing Zhou | 2026-07-19 | 2026-07-23 | 5 | Completed
| AR-034 | Establish WT04N stability (holding time) study protocol | Jing Zhou | 2026-05-07 | 2026-06-12 | 37 | Completed
|  | RSM Manufacture (AR01-SM2 / DF02N) |  | 2026-04-10 | 2026-07-24 | 106
Documentation | AR-035 | Documentation for AR-SM2 manufacture | Wenxxiang Zhou | 2026-04-10 | 2026-05-20 | 41 | Completed
| AR-036 | Update SM2 analytical method | Xinyi Zhao | 2026-05-11 | 2026-05-25 | 15 | Completed
AR01-SM2 Production (last step under GMP, 445kg) | AR-037 | AR01-9 (14 lots) production | Alex Xu | 2026-04-22 | 2026-06-24 | 64 | Completed
| AR-038 | SM2 (9 lots) production under GMP | Zongjun Liu | 2026-05-27 | 2026-07-15 | 50 | Completed
| AR-039 | Release test of SM2 (1-3 lots) | Jing Zhou | 2026-06-12 | 2026-06-20 | 9 | Completed
| AR-040 | Release test of SM2 (4-6 lots) | Jing Zhou | 2026-06-26 | 2026-07-04 | 9 | Completed
| AR-041 | Release test of SM2 (7-9 lots) | Jing Zhou | 2026-07-16 | 2026-07-24 | 9 | Completed
| AR-042 | Establish DF02N stability (holding time) study protocol | Jing Zhou | 2026-05-07 | 2026-06-12 | 37 | Completed
|  | Documentation before PPQ Manufacture |  | 2026-06-09 | 2026-08-08
Documentation | AR-043 | Scale-up Change for AS00N in Workshop A9 | Xubo Zheng | 2026-06-15 | 2026-07-10 | 26 | Completed
| AR-044 | Establish Validation Master Plan of AS00N(AR882) | Ling Lin | 2026-06-09 | 2026-07-25 | 47 | Completed
| AR-045 | Update IPC specs | Ling Lin | 2026-07-05 | 2026-07-20 | 16 | Completed
| AR-046 | Update intermediate specifications | Xinyi Zhao | 2026-07-05 | 2026-07-20 | 16 | Completed
| AR-047 | Update AS00N spec. | Ling Lin | 2026-07-05 | 2026-07-20 | 16 | Completed
| AR-048 | Establish the MBR of AS01N | Li Ji | 2026-06-26 | 2026-07-25 | 30 | Completed
| AR-049 | Establish the MBR of AS02N | Li Ji | 2026-06-30 | 2026-07-25 | 26 | Completed
| AR-050 | Establish the MBR of AS00N | Li Ji | 2026-07-03 | 2026-07-25 | 23 | Completed
| AR-051 | Establish PPQ protocol for AS00N(AR882) | Hongyang Ran | 2026-06-09 | 2026-07-25 | 47 | Completed
| AR-052 | Establish the drying profile study protocol for AS00N | Hongyang Ran | 2026-07-01 | 2026-07-25 | 25 | Completed
| AR-053 | Establish the homogeneity study protocol for AS00N | Xubo Zheng | 2026-07-01 | 2026-07-25 | 25 | Completed
| AR-054 | Establish the stability study protocol for AS00N | Jing Zhou | 2026-07-15 | 2026-08-08 | 25 | Completed
| AR-055 | Establish the holding time study protocol for AS01N and AS02N | Xubo Zheng | 2026-07-06 | 2026-07-25 | 20 | Completed
OOS Investigation on SM2 appearance variations
| AR-056 | Laboratory Investigation |  | 2026-07-14 | 2026-07-14 |  | Completed
| AR-057 | Production and sampling investigation |  | 2026-07-14 | 2026-07-16 |  | Completed
| AR-058 | Other investigation - use test |  | 2026-07-14 | 2026-07-20 |  | Completed
| AR-059 | Additional laboratory investigation - Iodine test of SM2 |  | 2026-07-14 | 2026-07-20 |  | Completed
| AR-060 | Investigations report (including CAPA) |  | 2026-07-20 | 2026-07-24 |  | Completed
| AR-061 | Change control |  | 2026-07-24 | 2026-07-25 |  | Completed
| AR-062 | Quality specification |  | 2026-07-25 | 2026-07-25 |  | Completed
| AR-063 | Test and release according to update spec. |  | 2026-07-25 | 2026-07-27 |  | Completed
Prospective Batch Manufacture
|  | INT-1 Prospective Production |  | 2026-08-01 | 2026-08-14 | 14 | Completed
INT-1 Production | AR-064 | INT-1 (prospective batch) prodution (Include cleaning) | Zongjun Liu | 2026-08-01 | 2026-08-14 | 14 | Completed
| AR-065 | Release test of INT-1(prospective batch) | Jing Zhou | 2026-08-07 | 2026-08-11 | 5 | Completed
|  | INT-2 Prospective Production |  | 2026-08-12 | 2026-08-29 | 18 | Completed
INT-2 Production | AR-066 | INT-2 (prospective batch) prodution (Include cleaning) | Zongjun Liu | 2026-08-12 | 2026-08-29 | 18 | Completed
| AR-067 | Release test of INT-2 (prospective batch) | Jing Zhou | 2026-08-20 | 2026-08-24 | 5 | Completed
|  | Unmilled AR882 Prospective Production |  | 2026-08-25 | 2026-09-10 | 17 | Completed
Unmilled AR882 Production | AR-068 | Unmilled AR882 (prospective batch) production (Include cleaning) | Zongjun Liu | 2026-08-25 | 2026-09-10 | 17 | Completed
| AR-069 | Release testing of Unmilled AR882 (prospective batch) | Jing Zhou | 2026-09-01 | 2026-09-07 | 7 | Completed
|  | Jet mill Prospective Production |  | 2026-09-08 | 2026-09-20 | 13 | Completed
Jet mill for pre-PPQ Production | AR-070 | Jet mill for prospective batch (Include cleaning) | Zongjun Liu | 2026-09-08 | 2026-09-17 | 10 | Completed
| AR-071 | Release test of AR882 (prospective batch) | Jing Zhou | 2026-09-10 | 2026-09-20 | 11 | Completed
| AR-072 | Establish PPQ interim report for AS00N(AR882) | Xubo Zheng | 2026-09-20 | 2026-09-24 | 5 | Ongoing
| AR-073 | Shipment of AR882 (Prospective batch) | Aiming Peng | 2026-09-25 | 2026-10-01 | 7 | To be start
|  | PPQ Manufacture |  | 2026-04-03 | 2027-01-31 | 304
|  | Materials purchasing |  | 2026-04-03 | 2026-07-20 | 109
Purchase | AR-074 | All materials purchasing and release | Xubo Zheng | 2026-04-03 | 2026-07-20 | 109 | Completed
|  | INT-1 PPQ Manufacture |  | 2026-09-29 | 2026-11-02 | 35 | To be start
INT-1 PPQ1 | AR-075 | INT-1 (batch2) production (Include cleaning) | Zongjun Liu | 2026-09-29 | 2026-10-12 | 14 | Completed
| AR-076 | Release test of INT-1 (batch2) | Jing Zhou | 2026-10-04 | 2026-10-08 | 5 | Completed
INT-1 PPQ2 | AR-077 | INT-1 (batch3) production | Zongjun Liu | 2026-10-09 | 2026-10-14 | 6 | Ongoing
| AR-078 | Release test of INT-1 (batch3) | Jing Zhou | 2026-10-14 | 2026-10-18 | 5 | Ongoing
INT-1 PPQ3 | AR-079 | INT-1 (batch4) production (Include cleaning) | Zongjun Liu | 2026-10-20 | 2026-11-02 | 14 | To be start
| AR-080 | Release test of INT-1 (batch4) | Jing Zhou | 2026-10-25 | 2026-10-30 | 6 | To be start
|  | INT-2 PPQ Manufacture |  | 2026-10-10 | 2026-11-27 | 49 | Ongoing
INT-2 PPQ1 | AR-081 | INT-2 (batch2) production (Include cleaning) | Zongjun Liu | 2026-10-10 | 2026-10-27 | 18 | Ongoing
| AR-082 | Release test of INT-2 (batch2) | Jing Zhou | 2026-10-18 | 2026-10-22 | 5 | To be start
INT-2 PPQ2 | AR-083 | INT-2 (batch3) production | Zongjun Liu | 2026-10-28 | 2026-11-04 | 8 | To be start
| AR-084 | Release test of INT-2 (batch3) | Jing Zhou | 2026-11-05 | 2026-11-09 | 5 | To be start
INT-2 PPQ3 | AR-085 | INT-2 (batch4) production (Include cleaning) | Zongjun Liu | 2026-11-10 | 2026-11-27 | 18 | To be start
| AR-086 | Release test of INT-2 (batch4) | Jing Zhou | 2026-11-18 | 2026-11-22 | 5 | To be start
|  | AR882 PPQ Manufacture |  | 2026-11-18 | 2027-01-17 | 61 | To be start
AR882-PPQ1 | AR-087 | Unmilled AR882 (batch2) production (Include cleaning) | Zongjun Liu | 2026-11-18 | 2026-12-04 | 17 | To be start
| AR-088 | Release testing of Unmilled AR882 (batch2) | Jing Zhou | 2026-11-25 | 2026-12-01 | 7 | To be start
| AR-089 | Jet mill for batch2 (Including cleaning) | Zongjun Liu | 2026-12-02 | 2026-12-11 | 10 | To be start
| AR-090 | Release test of AR882 (batch2) | Jing Zhou | 2026-12-04 | 2026-12-14 | 11 | To be start
AR882-PPQ2 | AR-091 | Unmilled AR882 (batch3) production | Zongjun Liu | 2026-12-05 | 2026-12-11 | 7 | To be start
| AR-092 | Release testing of Unmilled AR882 (batch3) | Jing Zhou | 2026-12-12 | 2026-12-18 | 7 | To be start
| AR-093 | Jet mill for batch3 | Zongjun Liu | 2026-12-19 | 2026-12-20 | 2 | To be start
| AR-094 | Release test of AR882 (batch3) | Jing Zhou | 2026-12-21 | 2026-12-31 | 11 | To be start
AR882-PPQ3 | AR-095 | Unmilled AR882 (batch4) production (Include cleaning) | Zongjun Liu | 2026-12-19 | 2027-01-04 | 17 | To be start
| AR-096 | Release testing of Unmilled AR882 (batch4) | Jing Zhou | 2026-12-26 | 2027-01-01 | 7 | To be start
| AR-097 | Jet mill for batch4 (Including Cleanging) | Zongjun Liu | 2027-01-02 | 2027-01-11 | 10 | To be start
| AR-98 | Release testing of AR882 (batch4) | Jing Zhou | 2027-01-04 | 2027-01-17 | 14 | To be start
|  | Reports, Release and Shipment |  | 2026-12-25 | 2027-01-31 | 38 | To be start
| AR-99 | Establish PPQ report for AS00N(AR882) | Xubo Zheng | 2027-01-04 | 2027-01-23 | 20 | To be start
| AR-100 | Establish the drying profile study report for AS00N | Xubo Zheng | 2026-12-25 | 2027-01-20 | 27 | To be start
| AR-101 | Establish the homogeneity study report for AS00N | Xubo Zheng | 2027-01-15 | 2027-01-23 | 9 | To be start
| AR-102 | Release of AR882 / AS00N | Richard Huang | 2027-01-24 | 2027-01-24 | 1 | To be start
| AR-103 | Shipment of AR882 / As00N | Aiming Peng | 2027-01-25 | 2027-01-31 | 7 | To be start
| AR-104 | Establish Validation Master Report of AS00N(AR882) | Ling Lin | 2027-02-18 | 2027-03-10 | 21 | To be start
Formulas:
Start Date = MIN([Start Date, row below]:E15)
Start Date = [Finish Date, row above]
Finish Date = MAX([Finish Date, row below]:F15)
Finish Date = MAX([Finish Date, row below]:[Finish Date, row below])
Status = IF([Finish Date]<>"","Completed",IF([Duration]=0,"To be start",IF(AND([Work Scope]<TODAY(),[Duration]<>100%),"Overdue","Ongoing")))

## 已完成-行动项 (hidden)
序列 | 内容 | 状态 | 开始日期 | 完成日期 | 责任人 | 备注
1 | 制定供应商审计计划，QA提供客供料RM1 & RM2引用客户审计报告的需求清单 | 已完成 | 2022-09-30 | 2022-10-12 | 吴春华，小兰 | 2022/10/12：QA 已经提供 PMO提醒客户提供客供料审计相关信息与资料
2 | 客户确认按照更换后的路线（AQCD）进行工艺开发，以前面2~3周对step2和step3进行工艺参数摸索获得的信息，在新步骤中确认，并以新产生的数据为基础finalize。（其他步骤未发生变化，请在现有变更的基础上评估变更后影响） | 已完成 | 2022-10-05 | 2022-10-23 | 沈海波
3 | 提供所需杂质时间计划表 | 已完成 | 2022-10-05 | 2022-10-15 | 韩叶华 | 2022/10/13: 已完成
4 | PV 所需设备 材质 时间计划表 | 已完成 | 2022-10-05 | 2022-10-15 | 沈海波 赵中良
5 | 客户提供客供料RM1 & RM2审计报告（QA已提供需求清单） | 已完成 | 2022-10-05 | 2022-10-30 | PMO
6 | RM3 供应商审计启动时间计划 | 已完成 | 2022-10-05 | 2022-10-20 | 王小兰 | 2022/10/13: 已给出相关意见，需要三批原料验证，与供应商沟通后，顺利的话审计周期需20天，供应商审计资料提前准备
7 | 统计RSM的批次，批量并制定与PV生产批对批的策略 | 已完成 | 2022-10-05 | 2022-10-12 | 赵中良，吴春华 | 2022/10/12：RSM 原料验证需要三批
8 | 丙基磺酰氯的供应商信息反馈给PMO | 已完成 | 2022-10-12 | 2022-10-20 | 沈海波 尹鹏 | 2022/10/20：研发提供备选的3家（ 丙基磺酰氯）采购供应商信息，如下：a)江西国化实业有限公司（目前生产批次使用的供应商）b) 寿光诺盟化工有限公司（已经提供500g小样）c) 上海玉雕化学技术有限公司（不能提供小样，且,吨位起订）
9 | 客户建议第二批 GMP 2月底放行-时间计划表需更新 | 已完成 | 2022-10-12 | 2022-10-20 |  | 2022/10/20：与客户确认后，时间么有问题
11 | 该批次中抽出部分产品进行 纯化+标化 后作为对照品（130 g +20 g 制剂），预计10.24 完成 | 已完成 | 2022-10-12 | 2022-10-24 | 韩叶华 沈海波 | 2022/10/24：已完成制备，COA已发给客户确认，并寄2.0 g给客户。2022/10/12：目前正在做50 g规模
13 | 博腾准备启动调查报告，调查成品磨粉后含量由98.8 %降为 98.2%的具体原因，同时收集与含量相关的数据反馈于客户，并同时进行返工结晶。 | 已完成 | 2022-10-12 | 2022-11-01 | 韩叶华 陈晓霖 | 2022/11/1：在全检放行。2022/10/22：D290-F再加工 R干品出料24.92 kg，预计25号磨粉小试。 2022/10/12：先返工，调查同时进行。2022/10/9:调查继续进行，样品返工纯化化，客户希望24号产品反馈至制剂端。 2022/9/30: QC初步调查没有问题，准备启动技术和研发调查 | 工艺原因：D290-B步骤产生的PMB副产物，在D290-B、D290-C、D290-D中未监测到，并且工艺去除能力有限，也未进行相应的纯化操作。导致该杂质进入到D290-F中，而D290-F的工艺对该杂质的去除能力也不高，而D290-F至D290步骤只是磨粉操作，没有除杂能力，最终导致D290成品含量偏低，其接近标准范围下限。D290-F工艺对杂质处理能力有限，不能完全将核磁图谱中6.5~7.0处是有的未知杂质完全去除，从而导致103582-105-00002(汉霖批次)含量偏低。
14 | QRA 研究中间体物料数量的预留计划 | 已完成 | 2022-10-12 | 2022-11-02 | 沈海波 | 2022/11/2：自己备料。2022/10/19：待沈海波与客户确定。
10 | 按照注册申报要求，提供RSM、关键物料的名称以及供应商信息 | 已完成 | 2022-10-20 | 2022-10-20 | 沈海波 | 2022/10/19；关键物料与客户进行沟通没有关键物料—跟TC客户沟通。供应商信息给PMO，反馈给采购提前收集相关数据。2022/10/12：需研发收集数据反馈 RM3 供应商信息
12 | 确认D290-A杂质信息 | 已完成 | 2022-10-26 | 2022-10-26 | 沈海波 尹鹏 | 2022/10/26：D290-A 两个杂质 给到分析50 g。
15 | 确认Demo 是否可以分段进行生产 | 已完成 | 2022-10-26 | 2022-10-27 | 张栋 | 2022/10/27：已确认分段方案可行
17 | RSM 分批排产计划 | 已完成 | 2022-10-26 | 2022-10-26 | 李祥福 | 2022/10/26: 四批生产for Demo,PV
18 | 与客户确认API 是否需要增加粗品结晶工艺 | 已完成 | 2022-10-26 | 2022-10-28 | 周琪 | 2022/10/28：与客户确认需要增加
16 | 关于RSM 分批计划，SPOC ,summer 内部讨论确认其可行性 | 已完成 | 2022-11-02 | 2022-11-02 | 张栋 | 邮件已确认
5 | 17 kg毒理批 生产计划 | 已完成 | 2022-10-12 | 2022-11-09 | 沈海波 赖伟 | 2022/11/9：曾泉文已经排产了。2022/10/19：报价的同时正在预约产能
7 | 最后2步的最终工艺确认工作（D290-D）转移至岩博团队 | 已完成 | 2022-10-12 | 2022-10-26 | 沈海波 陈岩 卢亮 | 2022/10/26：最后两步已转移至岩博团队，最终工艺确认正在进行。

## PV排产计划表-原始 (hidden)
设备 | 生产车间 | 步骤 | 状态 | 外观 | 体积/m³ | 单步周期 | 210446 | 技术批 | PV1 | PV2 | PV3 | PV设备（差异）
R-A2086（GL 1000L） | WS102 | D290-A | 中间体 | 固体 | 4 | 5 | 生产批次 | 1 | 1 | 2 | 3 | ——
C-A2106（Halar） | WS101 | [5 empty] | 投料量/KG
G-A1009（GL 3000L） | [6 empty] | 开始时间 | 2023-01-19 | 2023-03-30 | 2023-04-06 | 2023-04-13
[7 empty] | 结束时间 | 2023-01-23 | 2023-04-03 | 2023-04-10 | 2023-04-17
产出量/KG
R-A2087（GL 1500L） | WS102 | D290-B | 中间体 | 液体 | 4.5 | 4 | 生产批次 | 1 | 1 | 2 | 3 | ——
R-A2081（GL 3000L） | [6 empty] | 投料量/KG
[7 empty] | 开始时间 | 2023-01-30 | 2023-04-06 | 2023-04-21 | 2023-05-06
[7 empty] | 结束时间 | 2023-02-02 | 2023-04-09 | 2023-04-24 | 2023-05-09
产出量/KG
R-A2087（GL 1500L） | WS102 | D290-C湿品 | 中间体 | 固体 | 4.5 | 6 | 生产批次 | 1 | 1 | 2 | 3 | ——
R-A2081（GL 3000L） | [6 empty] | 投料量/KG
C-A2128（Halar） | [6 empty] | 开始时间 | 2023-02-05 | 2023-04-12 | 2023-04-27 | 2023-05-12
[7 empty] | 结束时间 | 2023-02-10 | 2023-04-17 | 2023-05-02 | 2023-05-17
产出量/KG
R-A2093（GL 2000L） | WS102 | D290-D | 中间体 | 固体 | 8 | 7 | 生产批次 | 1 | 1 | 2 | 3 | C-A2131（Halar φ800）
R-A2091（GL 3000L） | [6 empty] | 投料量/KG
C-A3105（Halar φ800）+压滤器 | [6 empty] | 开始时间 | 2023-02-13 | 2023-05-17 | 2023-05-25 | 2023-06-02
G-A2008（GL 3000L） | [6 empty] | 结束时间 | 2023-02-19 | 2023-05-23 | 2023-05-31 | 2023-06-08
产出量/KG
R-A2088（GL 1500L） | WS102 | D290-F乙酸乙酯溶液 | 中间体 | 液体 | 4.5 | 7 | 生产批次 | 1 | 1 | 2 | 3 | ——
R-A6088（GL 3000L） | [6 empty] | 投料量/KG
[7 empty] | 开始时间 | 2023-02-22 | 2023-05-27 | 2023-06-06 | 2023-06-16
[7 empty] | 结束时间 | 2023-02-28 | 2023-06-02 | 2023-06-12 | 2023-06-22
产出量/KG
R-A1016（GL 2000L） | WS101 | D290-F | 中间体 | 固体 | 4.08 | 6 | 生产批次 | 1 | 1 | 2 | 3 | ——
R-A1017（HC 2000L） | [6 empty] | 投料量/KG
C-A1086（HAC） | [6 empty] | 开始时间 | 2023-03-09 | 2023-06-10 | 2023-06-17 | 2023-06-24
B-A1192（HAC 75.6L） | [6 empty] | 结束时间 | 2023-03-14 | 2023-06-15 | 2023-06-22 | 2023-06-29
产出量/KG
B-A1193（气流粉碎机 SS） | WS101 | D290 | 成品 | 固体 | —— | 5 | 生产批次 | 1 | 1 | 2 | 3 | ——
投料量/KG
[7 empty] | 开始时间 | 2023-03-16 | 2023-06-29 | 2023-07-07 | 2023-07-15
[7 empty] | 结束时间 | 2023-03-20 | 2023-07-03 | 2023-07-11 | 2023-07-19
[7 empty] | 产出量/KG | 25 | 25 | 25 | 25

## 15 kg 毒理批排产计划表-221115 已完成 9.38 (hidden)
因上次25 kg 批次D290-A因收率低，重投了一锅得到的D290-A产品37 Kg 直接用于此次的毒理批生产,D290
15 kg毒理批产能计划如下:.
步骤 | 生产车间 | 计划生产时间 | 设备1 | 设备2
D290-C湿品 | 104车间 | 10.14~10.18 | R-A4028（GL 1000L） | R-A4023（GL 1500L）
D290-D粗湿品 | 104车间 | 10.18~10.21 | R-A4028（GL 1000L） | ——
D290-D湿品 | 304车间 | 10.21~10.23 | R-FA4067（GL 100L） | ——
D290-D | 304车间 | 10.23~10.25 | 根据项目进度随时跟进干燥设备
D290-F乙酸乙酯溶液 | 104车间 | 10.28~11.02 | R-A4028（GL 1000L） | ——
D290-F湿品 | 技术部公斤级实验室 | 11.02~11.05 | 50L玻璃釜*2 | ——
D290-F | 304 | 11.06~11.7 | 根据项目进度随时跟进干燥设备
D290 | 101 | 11.7~11.10 | B-A1193
(需要根据PSD判断是否需要做磨粉小试)
D290全检 |  | 11.10~11.15
(20221104)计划排产:
步骤 | 操作 | 车间 | 完成时间 | 耗时 | 备注
D290-F乙酸乙酯溶液
D290-F乙酸乙酯溶液 | 浓缩结束 | 104车间 | 2022-11-04 13:00
| 取样中控拿到结果 |  | 2022-11-04 20:00 | 7
| 压滤、过硅胶垫结束 |  | 2022-11-04 22:00 | 2
D290-F乙酸乙酯溶液
D290-F湿品
结晶1次 | 投料开始 | 106车间 | 2022-11-05 13:00
| 浓缩结束 |  | 2022-11-05 21:00 | 8
| 升温转晶结束 |  | 2022-11-06 03:00 | 6
| 降温结束 |  | 2022-11-06 08:00 | 5
| 结晶结束 |  | 2022-11-06 14:00 | 6
| 取样中控结束 |  | 2022-11-06 16:00 | 2 | 不等中控结果
| 压滤/离心 |  | 2022-11-06 19:00 | 5
| 湿品中控 |  | 2022-11-07 19:00 | 24 | 不等中控结果
结晶2次 | 投料 | 106车间 | 2022-11-06 19:00
| 浓缩 |  | 2022-11-07 05:00 | 10
| 升温转晶 |  | 2022-11-07 11:00 | 6
| 降温 |  | 2022-11-07 16:00 | 5
| 结晶 |  | 2022-11-07 22:00 | 6
| 取样中控 |  | 2022-11-08 | 2
| 压滤/离心 |  | 2022-11-08 05:00 | 5
| 湿品中控 |  | 2022-11-09 05:00 | 24 | 不等中控结果
干燥 | 投料 | 304车间 | 2022-11-08 08:00
| 升温干燥 |  | 2022-11-09 08:00 | 24
| 取样中控 |  | 2022-11-09 14:00 | 6
| 出料 |  | 2022-11-09 16:00 | 2
掺杂 | 投料 | 304 | 2022-11-10 16:00 | 24
| 取样中控 |  | 2022-11-11 02:00 | 10
磨粉 | 磨粉投料 | 101车间 | 2022-11-13 09:00
| 磨粉 |  | 2022-11-13 19:00 | 10